## Building
PIONEER LIBRARY SYSTEM Building Capital Improvement Plan
Project Name | Last insall | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY > 10 yrs | Total
HVAC Rooftop Unit (1 of 4) | 2013-11-22 | FY 2028: 15000 |  | 15000
HVAC Rooftop Unit (2 of 4) | 2013-11-22 | FY 2029: 15000 |  | 15000
HVAC Rooftop Unit (3 of 4) | 2013-11-22 | FY 2030: 15000 |  | 15000
HVAC Rooftop Unit (4 of 4) | 2013-11-22 | FY 2031: 15000 |  | 15000
Roof | 2013-12-06 | [10 empty] | 50000 | 50000
Sealcoat Driveway | 2018-07-25 | FY 2023: 5500; FY 2029: 5500 |  | 11000
Duct free split cooling system - Server Room moved to Garage 10/2021 | 2017-11-07 | FY 2027: 11000 |  | 11000
(1 of 2) Duct free split cooling system - Large mtg room | 2017-12-19 | FY 2028: 11000 |  | 11000
(2 of 2) Duct free split cooling system - Large mtg room | 2017-12-19 | [10 empty] | 11000 | 11000
40 gal Hot Water tank | 2019-02-13 | FY 2024: 3000 |  | 3000
Rheem Furnace | 2001-01-01 | FY 2023: 8000 |  | 8000
Generac Generator | 2004-03-01 | FY 2022: 15000 |  | 15000
Replace tile in hallway |  | FY 2022: 10000 |  | 10000
Parking Lot Repairs - Front | 2000-01-01 | FY 2025: 8000 |  | 8000
Parking Lot Repairs - Back | 2003-01-01 | FY 2030: 5000 |  | 5000
Parking Lot Repairs - NE side of Bldg | 2009-01-01 | [10 empty] | 3000 | 3000
|  | 25000 | 13500 | 3000 | 8000 | 0 | 11000 | 26000 | 20500 | 20000 | 15000 | 64000 | 206000
|  | FY 2028: Current Capital Improvement/Contingency Reserve @ 12/31/2020 |  | 55000
|  | FY 2028: Approved additional deposits to Reserve at 12/31/2021 |  | 45000
|  | FY 2029: Balance @ 12/31/2021 |  | 100000
[7 empty] | Addt'l YE deposits: |  | Deposits | Expenses | Balance
[8 empty] | 2022 | 20000 | 25000 | 95000
[8 empty] | 2023 | 10000 | 13500 | 91500
[8 empty] | 2024 | 10000 | 3000 | 98500
[8 empty] | 2025 | 10000 | 8000 | 100500
[8 empty] | 2026 | 10000 | 0 | 110500
[8 empty] | 2027 | 10000 | 11000 | 109500
[8 empty] | 2028 | 10000 | 26000 | 93500
[8 empty] | 2029 | 10000 | 20500 | 83000
[8 empty] | 2030 | 10000 | 20000 | 73000
[8 empty] | 2031 | 10000 | 15000 | 68000
Note on M9: Y2033
Note on M13: Y2032
Note on A16: Kelly Nemitz: Added to list 9/29/21 not on asset list Installed in 3/2004 total cost $10,394.36

## Sample Project Plan
Project Title:
Simple project plan outline.
Narrative:
Simple project plan outline.
Budget:
Item | Cost
One | 100
Two | 200
Three | 300
Four | 400
Total: | 1000
Timeline:
Phase | Month | Activity
One | January
Two | March
Three | April
Funding Souces:
Source | Amount
Source One | 100
Source Two | 200
Source Three | 300
Source Four | 400
Total: | 1000